## Summary
FIN·OS phone app — parity with the website
Source of truth: the 'Parity Tracker' sheet. Counts below are formulas. Last built 2026-10-12.
Area | Done | Partial | Pending | Blocked | Not planned | Total | % done (of planned)
Trackers & planners | 27 | 3 | 9 | 0 | 1 | 40 | 73.08%
Calculators | 2 | 0 | 88 | 0 | 0 | 90 | 2.222%
Learning & education | 0 | 0 | 51 | 0 | 0 | 51 | 0%
Markets & research | 2 | 0 | 18 | 1 | 0 | 21 | 9.524%
Portfolio & standalone apps | 2 | 0 | 7 | 0 | 1 | 10 | 22.22%
Arya AI | 2 | 0 | 7 | 0 | 0 | 9 | 22.22%
Platform & account | 5 | 0 | 11 | 0 | 0 | 16 | 31.25%
Release readiness | 3 | 2 | 6 | 6 | 0 | 17 | 23.53%
All areas | 43 | 5 | 197 | 7 | 2 | 254 | 18.06%
Open work by priority
Priority | Not done yet (Partial + Pending + Blocked) | Meaning
P0 | 8 | Release blockers — cannot ship without these
P1 | 5 | High value for daily use
P2 | 20 | Useful, after P1
P3 | 176 | Long tail / nice to have
How to read '% done': Done counts 1, Partial counts 0.5, Not planned is left out of the denominator.
Counts are of rows in the tracker, not of effort: one row can be a 30-minute port or a multi-day feature (see Effort).

## Parity Tracker
ID | Area | Feature | Website source | Phone status | Priority | Effort | Build order | Planned phone location | Notes | Updated
T-01 | Trackers & planners | Portfolio Growth Simulator | html/portfolio.html | Pending | P3 | M |  | tools/… |  | 2026-10-12
T-02 | Trackers & planners | Budget Forecast (pace, AI forecast) | html/budget-forecast.html | Partial | P2 | M |  | tracker/budget | Category limits, pace and suggestions are done; the forecast view is not | 2026-10-12
T-03 | Trackers & planners | Subscription Tracker | html/subscription-tracker.html | Done | P2 | M |  | tracker/subscriptions | Parity-tested against js/finos-subscriptions.js | 2026-10-12
T-04 | Trackers & planners | Credit Score Tracker | html/credit-score.html | Done | P2 | S |  | tools/credit | CIBIL band, home-loan rate impact, ranked improvement tips; nothing assumed when a figure was not typed; parity-tested vs js/finos-credit-score.js | 2026-10-12
T-05 | Trackers & planners | Crypto Tracker | html/crypto-tracker.html | Done | P2 | M |  | tracker/crypto | Holdings, P&L, 31.2% tax on each coin's gain, 1% TDS what-if; prices are typed (never fetched); parity-tested vs js/finos-crypto-tracker.js | 2026-10-12
T-06 | Trackers & planners | Debt Optimizer (avalanche / snowball) | html/debt-optimizer.html | Done | P1 | M | 7 | tools/debt | Avalanche vs snowball + home-loan prepayment impact; shares balances with Net Worth; parity-tested vs js/finos-debt-optimizer.js | 2026-10-12
T-07 | Trackers & planners | Emergency Fund Tracker | html/emergency-fund.html | Done | P2 | S |  | tracker/emergency |  | 2026-10-12
T-08 | Trackers & planners | EPF Tracker | html/epf-tracker.html | Done | P2 | M |  | tracker/epf |  | 2026-10-12
T-09 | Trackers & planners | Fixed Income (FD) Tracker | html/fd-tracker.html | Done | P1 | M | 9 | tracker/fixed | FD, RD, PPF, NSC, SCSS, Sukanya, bonds, post office; same finos_fd_portfolio key as the web; parity-tested; RD 0% division guarded | 2026-10-12
T-10 | Trackers & planners | Financial Calendar (+ reminders) | html/financial-calendar.html | Partial | P1 | L | 11 | tools/calendar | Month grid, day detail, coming-up list, summary cards: SIP, deposit maturities (real terms), insurance, goals, subscriptions, tax dates; parity-tested. Phone notifications NOT built: need an OS notification permission, which the privacy guard test currently forbids (owner decision). | 2026-10-12
T-11 | Trackers & planners | Financial Command Hub | html/financial-hub.html | Not planned | P3 | S |  |  | Dashboard + Track tab already do this job | 2026-10-12
T-12 | Trackers & planners | Goal Optimizer | html/goal-optimizer.html | Done | P2 | M |  | tools/goalopt (from Goals) | Inflation-adjusted SIP per goal, priority score, feasibility vs what you can invest, competing-goal conflicts; parity-tested vs js/finos-goal-optimizer.js. Website corrected in the same pass: saved money compounds as today's rupees (it was taken as a % of the inflated target, counting inflation twice). | 2026-10-12
T-13 | Trackers & planners | Gold Tracker | html/gold-tracker.html | Done | P1 | M | 10 | tracker/gold | Physical, SGB, gold ETF, gold MF; user-typed price only (no invented rate); coupon; parity-tested vs js/finos-gold-tracker.js | 2026-10-12
T-14 | Trackers & planners | Home Loan EMI Planner | html/home-loan.html | Done | P1 | M | 8 | tools/homeloan | EMI, amortisation, affordability, 24(b)/80C deductions, prepayment impact; parity-tested. Website's PMAY-CLSS 'eligible' banner deliberately not ported (scheme bands ended); writes loan keys only on 'Save as my home loan'. | 2026-10-12
T-15 | Trackers & planners | Insurance Hub (directory, compare) | html/insurance-hub.html | Partial | P2 | M |  | tracker/insurance | Policies, gaps and renewals are done; directory/compare is not | 2026-10-12
T-16 | Trackers & planners | ITR Filing Prep Kit | html/itr-summary.html | Done | P2 | M |  | tools/itr (from Tax planner) | Income, 80C itemised, 80CCD/80D/24(b)/80E/80TTA, both regimes, TDS and balance/refund; the calculation is sliced unchanged from js/finos-itr-summary.js and parity-tested; figures live under the website's keys. Capital gains and surcharge are not in this worksheet (the Tax Planner has them). | 2026-10-12
T-17 | Trackers & planners | Life Insurance Need Calculator | html/life-cover.html | Done | P2 | S |  | tools/lifecover (from Insurance) | Human life value + income replacement + debts − existing cover, status band, rough premium illustration; parity-tested vs js/finos-life-cover.js; prefilled from income, spending, policies and loans. | 2026-10-12
T-18 | Trackers & planners | Life Goals Planner | html/life-goals-planner.html | Pending | P2 | M |  | tracker/goals |  | 2026-10-12
T-19 | Trackers & planners | Mutual Fund Intelligence | html/mf-intelligence.html | Pending | P2 | L |  | markets/mf |  | 2026-10-12
T-20 | Trackers & planners | Net Worth Tracker | html/net-worth.html | Done | P2 | M |  | tracker/networth |  | 2026-10-12
T-21 | Trackers & planners | NPS Tracker | html/nps-tracker.html | Done | P2 | M |  | tracker/nps |  | 2026-10-12
T-22 | Trackers & planners | Passive Income Tracker | html/passive-income.html | Done | P2 | S |  | tracker/passive | Streams (dividend, FD, rental, SWP, SGB, other), coverage of monthly spending, freedom milestones, what-if, extra corpus at 4%; totals parity-tested vs js/finos-passive-income.js; FD/SGB seed lines are labelled as estimates. | 2026-10-12
T-23 | Trackers & planners | Portfolio Rebalancer | html/portfolio-rebalancer.html | Done | P2 | M |  | tools/rebalance | Six asset classes from the other trackers, target presets + editor, drift and action per class, new-money split; parity-tested vs js/finos-rebalancer.js. Differences: empty portfolio is not flagged, property and govt savings are advised as 'send new money elsewhere'. | 2026-10-12
T-24 | Trackers & planners | PPF & Small Savings Tracker | html/ppf-tracker.html | Done | P2 | M |  | tracker/ppf |  | 2026-10-12
T-25 | Trackers & planners | Real Estate Intelligence | html/real-estate.html | Pending | P3 | M |  | tools/real-estate |  | 2026-10-12
T-26 | Trackers & planners | Retirement Planner (Monte Carlo success odds) | html/retirement-planner.html | Done | P1 | L | 3 | tools/retirement | Built: corpus by source, 25× need, gap, income, Monte Carlo odds, fan chart, SIP solver. Engine identical to js/finos-montecarlo.js (40 random configs) and plan arithmetic identical on 400 random profiles. | 2026-10-12
T-27 | Trackers & planners | Salary Optimizer (CTC restructure) | html/salary-optimizer.html | Done | P1 | M | 5 | tools/salary | CTC breakup → gross, HRA three-way minimum, tax in both regimes, take-home, restructuring tips; parity-tested. Take-home becomes income only on tap (the website overwrites finos_monthly_income on every render). | 2026-10-12
T-28 | Trackers & planners | SIP Step-Up Planner | html/sip-stepup.html | Done | P1 | S | 6 | tools/stepup | Flat vs stepped-up SIP, scenario cards (5/10/15/20%), corpus chart, year table, milestones; parity-tested vs js/finos-sip-stepup.js incl. out-of-range inputs | 2026-10-12
T-29 | Trackers & planners | Tax Loss / Gain Harvesting | html/tax-harvest.html | Pending | P2 | M |  | tools/tax-harvest | Needs holdings with purchase dates | 2026-10-12
T-30 | Trackers & planners | Bonus & Windfall Allocator | html/windfall.html | Done | P2 | S |  | tools/windfall | Same waterfall as js/finos-windfall.js (parity-tested on 1,000 households) plus bonus/RSU tax impact; unknown spending is flagged instead of silently assuming ₹50,000; property note updated to the July 2024 rules. | 2026-10-12
T-31 | Trackers & planners | Tax (regime compare, Tax Savings Tracker, Tax Planner) | html/tax.html | Done | P1 | L | 4 | tools/tax + tools/taxplanner | Savings tracker (headroom per section) and the full Tax Planner (both regimes with surcharge, HRA, 80C/80D/NPS/24(b), LTCG/STCG, action list); parity-tested vs js/finos-tax-calc.js. Web surcharge fixed in the same pass (taxable income, new-regime top rate 25%). | 2026-10-12
T-32 | Trackers & planners | Money Score | html/money-score.html | Done | P1 | L |  | tools/score | Parity-tested against js/finos-money-score.js | 2026-10-12
T-33 | Trackers & planners | Future Loss / System Leak | html/system-leak.html | Done | P1 | M | 12 | tools/leak | Monthly leak from the ledger + subscriptions, 10/20/30-year future value, redirect share; parity-tested vs js/finos-leak.js | 2026-10-12
T-34 | Trackers & planners | Import bank statement | html/import-statement.html | Done | P1 | M |  | tracker/import |  | 2026-10-12
T-35 | Trackers & planners | Budget & transactions (track finances) | html/track-finances.html | Done | P1 | L |  | tracker/budget + transactions | Quick-log and recurring entries are phone-only extras | 2026-10-12
T-36 | Trackers & planners | Financial Health Score (7 pillars) | js/finos-health-score.js | Done | P1 | M |  | tracker/health |  | 2026-10-12
T-37 | Trackers & planners | Financial Report | html/financial-report.html | Pending | P3 | M |  | tools/report |  | 2026-10-12
T-38 | Trackers & planners | Couple Finance | html/couple-finance.html | Pending | P3 | L |  | tools/couple | Needs the couple_* Supabase tables | 2026-10-12
T-39 | Trackers & planners | Benchmarking (vs similar profiles) | html/benchmarking.html | Pending | P3 | M |  | tools/benchmark |  | 2026-10-12
T-40 | Trackers & planners | Document AI (upload and extract) | html/document-ai.html | Pending | P3 | L |  | tools/documents | Backend: document-ai service | 2026-10-12
C-01 | Calculators | Banking & Fixed Income — bond | calculators/banking & fixed income/bond.html | Pending | P3 | S |  | calculators/bond | Pure formula; port + parity test | 2026-10-12
C-02 | Calculators | Banking & Fixed Income — epf | calculators/banking & fixed income/epf.html | Pending | P3 | S |  | calculators/epf | Pure formula; port + parity test | 2026-10-12
C-03 | Calculators | Banking & Fixed Income — fd | calculators/banking & fixed income/fd.html | Pending | P3 | S |  | calculators/fd | Pure formula; port + parity test | 2026-10-12
C-04 | Calculators | Banking & Fixed Income — nps | calculators/banking & fixed income/nps.html | Pending | P3 | S |  | calculators/nps | Pure formula; port + parity test | 2026-10-12
C-05 | Calculators | Banking & Fixed Income — postoffice | calculators/banking & fixed income/postoffice.html | Pending | P3 | S |  | calculators/postoffice | Pure formula; port + parity test | 2026-10-12
C-06 | Calculators | Banking & Fixed Income — ppf | calculators/banking & fixed income/ppf.html | Pending | P3 | S |  | calculators/ppf | Pure formula; port + parity test | 2026-10-12
C-07 | Calculators | Banking & Fixed Income — rd | calculators/banking & fixed income/rd.html | Pending | P3 | S |  | calculators/rd | Pure formula; port + parity test | 2026-10-12
C-08 | Calculators | Banking & Fixed Income — savingsinvestment | calculators/banking & fixed income/savingsinvestment.html | Pending | P3 | S |  | calculators/savingsinvestment | Pure formula; port + parity test | 2026-10-12
C-09 | Calculators | Banking & Fixed Income — scss | calculators/banking & fixed income/scss.html | Pending | P3 | S |  | calculators/scss | Pure formula; port + parity test | 2026-10-12
C-10 | Calculators | Banking & Fixed Income — ssy | calculators/banking & fixed income/ssy.html | Pending | P3 | S |  | calculators/ssy | Pure formula; port + parity test | 2026-10-12
C-11 | Calculators | Core-Thinking — compounding-visualizer | calculators/core-thinking/compounding-visualizer.html | Pending | P3 | S |  | calculators/compounding-visualizer | Pure formula; port + parity test | 2026-10-12
C-12 | Calculators | Core-Thinking — financial-age-calculator | calculators/core-thinking/financial-age-calculator.html | Pending | P3 | S |  | calculators/financial-age-calculator | Pure formula; port + parity test | 2026-10-12
C-13 | Calculators | Core-Thinking — inflation-impact | calculators/core-thinking/inflation-impact.html | Pending | P3 | S |  | calculators/inflation-impact | Pure formula; port + parity test | 2026-10-12
C-14 | Calculators | Core-Thinking — money-behavior-analyzer | calculators/core-thinking/money-behavior-analyzer.html | Pending | P3 | S |  | calculators/money-behavior-analyzer | Pure formula; port + parity test | 2026-10-12
C-15 | Calculators | Core-Thinking — opportunity-cost | calculators/core-thinking/opportunity-cost.html | Pending | P3 | S |  | calculators/opportunity-cost | Pure formula; port + parity test | 2026-10-12
C-16 | Calculators | Core-Thinking — purchasing-power-loss | calculators/core-thinking/purchasing-power-loss.html | Pending | P3 | S |  | calculators/purchasing-power-loss | Pure formula; port + parity test | 2026-10-12
C-17 | Calculators | Core-Thinking — real-rate-of-return | calculators/core-thinking/real-rate-of-return.html | Pending | P3 | S |  | calculators/real-rate-of-return | Pure formula; port + parity test | 2026-10-12
C-18 | Calculators | Core-Thinking — risk-vs-reward | calculators/core-thinking/risk-vs-reward.html | Pending | P3 | S |  | calculators/risk-vs-reward | Pure formula; port + parity test | 2026-10-12
C-19 | Calculators | Core-Thinking — time-value-of-money | calculators/core-thinking/time-value-of-money.html | Pending | P3 | S |  | calculators/time-value-of-money | Pure formula; port + parity test | 2026-10-12
C-20 | Calculators | Core-Thinking — wealth-vs-income-gap | calculators/core-thinking/wealth-vs-income-gap.html | Pending | P3 | S |  | calculators/wealth-vs-income-gap | Pure formula; port + parity test | 2026-10-12
C-21 | Calculators | Desi Reality Check — buyhouse | calculators/desi reality check/buyhouse.html | Pending | P3 | S |  | calculators/buyhouse | Pure formula; port + parity test | 2026-10-12
C-22 | Calculators | Desi Reality Check — childedu | calculators/desi reality check/childedu.html | Pending | P3 | S |  | calculators/childedu | Pure formula; port + parity test | 2026-10-12
C-23 | Calculators | Desi Reality Check — creditaddiction | calculators/desi reality check/creditaddiction.html | Pending | P3 | S |  | calculators/creditaddiction | Pure formula; port + parity test | 2026-10-12
C-24 | Calculators | Desi Reality Check — emidiease | calculators/desi reality check/emidiease.html | Pending | P3 | S |  | calculators/emidiease | Pure formula; port + parity test | 2026-10-12
C-25 | Calculators | Desi Reality Check — govvspvt | calculators/desi reality check/govvspvt.html | Pending | P3 | S |  | calculators/govvspvt | Pure formula; port + parity test | 2026-10-12
C-26 | Calculators | Desi Reality Check — lifestyle | calculators/desi reality check/lifestyle.html | Pending | P3 | S |  | calculators/lifestyle | Pure formula; port + parity test | 2026-10-12
C-27 | Calculators | Desi Reality Check — logkyakahenge | calculators/desi reality check/logkyakahenge.html | Pending | P3 | S |  | calculators/logkyakahenge | Pure formula; port + parity test | 2026-10-12
C-28 | Calculators | Desi Reality Check — middleclass | calculators/desi reality check/middleclass.html | Pending | P3 | S |  | calculators/middleclass | Pure formula; port + parity test | 2026-10-12
C-29 | Calculators | Desi Reality Check — parental | calculators/desi reality check/parental.html | Pending | P3 | S |  | calculators/parental | Pure formula; port + parity test | 2026-10-12
C-30 | Calculators | Desi Reality Check — shaadicost | calculators/desi reality check/shaadicost.html | Pending | P3 | S |  | calculators/shaadicost | Pure formula; port + parity test | 2026-10-12
C-31 | Calculators | Financial Health — emergencyfund | calculators/financial health/emergencyfund.html | Pending | P3 | S |  | calculators/emergencyfund | Pure formula; port + parity test | 2026-10-12
C-32 | Calculators | Financial Health — expenseratio | calculators/financial health/expenseratio.html | Pending | P3 | S |  | calculators/expenseratio | Pure formula; port + parity test | 2026-10-12
C-33 | Calculators | Financial Health — insurancecoverage | calculators/financial health/insurancecoverage.html | Pending | P3 | S |  | calculators/insurancecoverage | Pure formula; port + parity test | 2026-10-12
C-34 | Calculators | Financial Health — lifestyle | calculators/financial health/lifestyle.html | Pending | P3 | S |  | calculators/lifestyle | Pure formula; port + parity test | 2026-10-12
C-35 | Calculators | Financial Health — networth | calculators/financial health/networth.html | Pending | P3 | S |  | calculators/networth | Pure formula; port + parity test | 2026-10-12
C-36 | Calculators | Financial Health — savings | calculators/financial health/savings.html | Pending | P3 | S |  | calculators/savings | Pure formula; port + parity test | 2026-10-12
C-37 | Calculators | Investment & Wealth — assetalloc | calculators/investment & wealth/assetalloc.html | Pending | P3 | S |  | calculators/assetalloc | Pure formula; port + parity test | 2026-10-12
C-38 | Calculators | Investment & Wealth — cagr | calculators/investment & wealth/cagr.html | Pending | P3 | S |  | calculators/cagr | Pure formula; port + parity test | 2026-10-12
C-39 | Calculators | Investment & Wealth — dividend | calculators/investment & wealth/dividend.html | Pending | P3 | S |  | calculators/dividend | Pure formula; port + parity test | 2026-10-12
C-40 | Calculators | Investment & Wealth — etf | calculators/investment & wealth/etf.html | Pending | P3 | S |  | calculators/etf | Pure formula; port + parity test | 2026-10-12
C-41 | Calculators | Investment & Wealth — goalbased | calculators/investment & wealth/goalbased.html | Pending | P3 | S |  | calculators/goalbased | Pure formula; port + parity test | 2026-10-12
C-42 | Calculators | Investment & Wealth — lupsum | calculators/investment & wealth/lupsum.html | Pending | P3 | S |  | calculators/lupsum | Pure formula; port + parity test | 2026-10-12
C-43 | Calculators | Investment & Wealth — mutualfunds | calculators/investment & wealth/mutualfunds.html | Pending | P3 | S |  | calculators/mutualfunds | Pure formula; port + parity test | 2026-10-12
C-44 | Calculators | Investment & Wealth — portfolio | calculators/investment & wealth/portfolio.html | Pending | P3 | S |  | calculators/portfolio | Pure formula; port + parity test | 2026-10-12
C-45 | Calculators | Investment & Wealth — rebalancing | calculators/investment & wealth/rebalancing.html | Pending | P3 | S |  | calculators/rebalancing | Pure formula; port + parity test | 2026-10-12
C-46 | Calculators | Investment & Wealth — rollingreturns | calculators/investment & wealth/rollingreturns.html | Pending | P3 | S |  | calculators/rollingreturns | Pure formula; port + parity test | 2026-10-12
C-47 | Calculators | Investment & Wealth — sip-optimizer | calculators/investment & wealth/sip-optimizer.html | Pending | P3 | S |  | calculators/sip-optimizer | Pure formula; port + parity test | 2026-10-12
C-48 | Calculators | Investment & Wealth — sip | calculators/investment & wealth/sip.html | Pending | P3 | S |  | calculators/sip | Pure formula; port + parity test | 2026-10-12
C-49 | Calculators | Investment & Wealth — stepup | calculators/investment & wealth/stepup.html | Pending | P3 | S |  | calculators/stepup | Pure formula; port + parity test | 2026-10-12
C-50 | Calculators | Investment & Wealth — swp | calculators/investment & wealth/swp.html | Pending | P3 | S |  | calculators/swp | Pure formula; port + parity test | 2026-10-12
C-51 | Calculators | Investment & Wealth — taxadj | calculators/investment & wealth/taxadj.html | Pending | P3 | S |  | calculators/taxadj | Pure formula; port + parity test | 2026-10-12
C-52 | Calculators | Investment & Wealth — xirr | calculators/investment & wealth/xirr.html | Pending | P3 | S |  | calculators/xirr | Pure formula; port + parity test | 2026-10-12
C-53 | Calculators | Loans, Debt & Emi — car | calculators/loans, debt & emi/car.html | Pending | P3 | S |  | calculators/car | Pure formula; port + parity test | 2026-10-12
C-54 | Calculators | Loans, Debt & Emi — creditcard | calculators/loans, debt & emi/creditcard.html | Pending | P3 | S |  | calculators/creditcard | Pure formula; port + parity test | 2026-10-12
C-55 | Calculators | Loans, Debt & Emi — debtsnow | calculators/loans, debt & emi/debtsnow.html | Pending | P3 | S |  | calculators/debtsnow | Pure formula; port + parity test | 2026-10-12
C-56 | Calculators | Loans, Debt & Emi — education | calculators/loans, debt & emi/education.html | Pending | P3 | S |  | calculators/education | Pure formula; port + parity test | 2026-10-12
C-57 | Calculators | Loans, Debt & Emi — emi | calculators/loans, debt & emi/emi.html | Pending | P3 | S |  | calculators/emi | Pure formula; port + parity test | 2026-10-12
C-58 | Calculators | Loans, Debt & Emi — emiprepay | calculators/loans, debt & emi/emiprepay.html | Pending | P3 | S |  | calculators/emiprepay | Pure formula; port + parity test | 2026-10-12
C-59 | Calculators | Loans, Debt & Emi — home | calculators/loans, debt & emi/home.html | Pending | P3 | S |  | calculators/home | Pure formula; port + parity test | 2026-10-12
C-60 | Calculators | Loans, Debt & Emi — interest | calculators/loans, debt & emi/interest.html | Pending | P3 | S |  | calculators/interest | Pure formula; port + parity test | 2026-10-12
C-61 | Calculators | Loans, Debt & Emi — loaneligibility | calculators/loans, debt & emi/loaneligibility.html | Pending | P3 | S |  | calculators/loaneligibility | Pure formula; port + parity test | 2026-10-12
C-62 | Calculators | Loans, Debt & Emi — loantenure | calculators/loans, debt & emi/loantenure.html | Pending | P3 | S |  | calculators/loantenure | Pure formula; port + parity test | 2026-10-12
C-63 | Calculators | Loans, Debt & Emi — personal | calculators/loans, debt & emi/personal.html | Pending | P3 | S |  | calculators/personal | Pure formula; port + parity test | 2026-10-12
C-64 | Calculators | Loans, Debt & Emi — prepayinvest | calculators/loans, debt & emi/prepayinvest.html | Done | P2 | S |  | tools/prepay | Parity-tested | 2026-10-12
C-65 | Calculators | Retirement & Life Planning — annuity | calculators/retirement & life planning/annuity.html | Pending | P3 | S |  | calculators/annuity | Pure formula; port + parity test | 2026-10-12
C-66 | Calculators | Retirement & Life Planning — healthcare | calculators/retirement & life planning/healthcare.html | Pending | P3 | S |  | calculators/healthcare | Pure formula; port + parity test | 2026-10-12
C-67 | Calculators | Retirement & Life Planning — lifeexpentancy | calculators/retirement & life planning/lifeexpentancy.html | Pending | P3 | S |  | calculators/lifeexpentancy | Pure formula; port + parity test | 2026-10-12
C-68 | Calculators | Retirement & Life Planning — longevity | calculators/retirement & life planning/longevity.html | Pending | P3 | S |  | calculators/longevity | Pure formula; port + parity test | 2026-10-12
C-69 | Calculators | Retirement & Life Planning — pensiongap | calculators/retirement & life planning/pensiongap.html | Pending | P3 | S |  | calculators/pensiongap | Pure formula; port + parity test | 2026-10-12
C-70 | Calculators | Retirement & Life Planning — postretirement | calculators/retirement & life planning/postretirement.html | Pending | P3 | S |  | calculators/postretirement | Pure formula; port + parity test | 2026-10-12
C-71 | Calculators | Retirement & Life Planning — retirement | calculators/retirement & life planning/retirement.html | Pending | P3 | S |  | calculators/retirement | Pure formula; port + parity test | 2026-10-12
C-72 | Calculators | Tax & Salary — 80c | calculators/tax & salary/80c.html | Pending | P3 | S |  | calculators/80c | Pure formula; port + parity test | 2026-10-12
C-73 | Calculators | Tax & Salary — captalgains | calculators/tax & salary/captalgains.html | Pending | P3 | S |  | calculators/captalgains | Pure formula; port + parity test | 2026-10-12
C-74 | Calculators | Tax & Salary — gratuity | calculators/tax & salary/gratuity.html | Pending | P3 | S |  | calculators/gratuity | Pure formula; port + parity test | 2026-10-12
C-75 | Calculators | Tax & Salary — hra | calculators/tax & salary/hra.html | Pending | P3 | S |  | calculators/hra | Pure formula; port + parity test | 2026-10-12
C-76 | Calculators | Tax & Salary — income | calculators/tax & salary/income.html | Pending | P3 | S |  | calculators/income | Pure formula; port + parity test | 2026-10-12
C-77 | Calculators | Tax & Salary — inhand | calculators/tax & salary/inhand.html | Pending | P3 | S |  | calculators/inhand | Pure formula; port + parity test | 2026-10-12
C-78 | Calculators | Tax & Salary — leave | calculators/tax & salary/leave.html | Pending | P3 | S |  | calculators/leave | Pure formula; port + parity test | 2026-10-12
C-79 | Calculators | Tax & Salary — offercompare | calculators/tax & salary/offercompare.html | Done | P2 | S |  | tools/offers | Parity-tested | 2026-10-12
C-80 | Calculators | Tax & Salary — oldnew | calculators/tax & salary/oldnew.html | Pending | P3 | S |  | calculators/oldnew | Pure formula; port + parity test | 2026-10-12
C-81 | Calculators | Tax & Salary — professional | calculators/tax & salary/professional.html | Pending | P3 | S |  | calculators/professional | Pure formula; port + parity test | 2026-10-12
C-82 | Calculators | Tax & Salary — shortlong | calculators/tax & salary/shortlong.html | Pending | P3 | S |  | calculators/shortlong | Pure formula; port + parity test | 2026-10-12
C-83 | Calculators | Trading & Markets — breakeven | calculators/trading & markets/breakeven.html | Pending | P3 | S |  | calculators/breakeven | Pure formula; port + parity test | 2026-10-12
C-84 | Calculators | Trading & Markets — brokerage | calculators/trading & markets/brokerage.html | Pending | P3 | S |  | calculators/brokerage | Pure formula; port + parity test | 2026-10-12
C-85 | Calculators | Trading & Markets — futurespl | calculators/trading & markets/futurespl.html | Pending | P3 | S |  | calculators/futurespl | Pure formula; port + parity test | 2026-10-12
C-86 | Calculators | Trading & Markets — margin | calculators/trading & markets/margin.html | Pending | P3 | S |  | calculators/margin | Pure formula; port + parity test | 2026-10-12
C-87 | Calculators | Trading & Markets — options | calculators/trading & markets/options.html | Pending | P3 | S |  | calculators/options | Pure formula; port + parity test | 2026-10-12
C-88 | Calculators | Trading & Markets — positionsize | calculators/trading & markets/positionsize.html | Pending | P3 | S |  | calculators/positionsize | Pure formula; port + parity test | 2026-10-12
C-89 | Calculators | Trading & Markets — riskper | calculators/trading & markets/riskper.html | Pending | P3 | S |  | calculators/riskper | Pure formula; port + parity test | 2026-10-12
C-90 | Calculators | Trading & Markets — volatility | calculators/trading & markets/volatility.html | Pending | P3 | S |  | calculators/volatility | Pure formula; port + parity test | 2026-10-12
L-01 | Learning & education | Learn: analysis | html/learn-analysis.html | Pending | P3 | M |  | learn/analysis | Content-heavy; candidate for the in-app web view | 2026-10-12
L-02 | Learning & education | Learn: commodity | html/learn-commodity.html | Pending | P3 | M |  | learn/commodity | Content-heavy; candidate for the in-app web view | 2026-10-12
L-03 | Learning & education | Learn: crypto | html/learn-crypto.html | Pending | P3 | M |  | learn/crypto | Content-heavy; candidate for the in-app web view | 2026-10-12
L-04 | Learning & education | Learn: debt | html/learn-debt.html | Pending | P3 | M |  | learn/debt | Content-heavy; candidate for the in-app web view | 2026-10-12
L-05 | Learning & education | Learn: equity | html/learn-equity.html | Pending | P3 | M |  | learn/equity | Content-heavy; candidate for the in-app web view | 2026-10-12
L-06 | Learning & education | Learn: etf | html/learn-etf.html | Pending | P3 | M |  | learn/etf | Content-heavy; candidate for the in-app web view | 2026-10-12
L-07 | Learning & education | Learn: fno | html/learn-fno.html | Pending | P3 | M |  | learn/fno | Content-heavy; candidate for the in-app web view | 2026-10-12
L-08 | Learning & education | Learn: forex | html/learn-forex.html | Pending | P3 | M |  | learn/forex | Content-heavy; candidate for the in-app web view | 2026-10-12
L-09 | Learning & education | Learn: fundamental | html/learn-fundamental.html | Pending | P3 | M |  | learn/fundamental | Content-heavy; candidate for the in-app web view | 2026-10-12
L-10 | Learning & education | Learn: indicators | html/learn-indicators.html | Pending | P3 | M |  | learn/indicators | Content-heavy; candidate for the in-app web view | 2026-10-12
L-11 | Learning & education | Learn: insurance | html/learn-insurance.html | Pending | P3 | M |  | learn/insurance | Content-heavy; candidate for the in-app web view | 2026-10-12
L-12 | Learning & education | Learn: metrics | html/learn-metrics.html | Pending | P3 | M |  | learn/metrics | Content-heavy; candidate for the in-app web view | 2026-10-12
L-13 | Learning & education | Learn: mf | html/learn-mf.html | Pending | P3 | M |  | learn/mf | Content-heavy; candidate for the in-app web view | 2026-10-12
L-14 | Learning & education | Learn: money-market | html/learn-money-market.html | Pending | P3 | M |  | learn/money-market | Content-heavy; candidate for the in-app web view | 2026-10-12
L-15 | Learning & education | Learn: technical | html/learn-technical.html | Pending | P3 | M |  | learn/technical | Content-heavy; candidate for the in-app web view | 2026-10-12
L-16 | Learning & education | Insight: debt | html/insight-debt.html | Pending | P3 | S |  | learn/insight-debt |  | 2026-10-12
L-17 | Learning & education | Insight: emi | html/insight-emi.html | Pending | P3 | S |  | learn/insight-emi |  | 2026-10-12
L-18 | Learning & education | Insight: inflation | html/insight-inflation.html | Pending | P3 | S |  | learn/insight-inflation |  | 2026-10-12
L-19 | Learning & education | Insight: rbi | html/insight-rbi.html | Pending | P3 | S |  | learn/insight-rbi |  | 2026-10-12
L-20 | Learning & education | Insight: sip | html/insight-sip.html | Pending | P3 | S |  | learn/insight-sip |  | 2026-10-12
L-21 | Learning & education | Finance 101 | html/finance101.html | Pending | P3 | M |  | learn/finance101 |  | 2026-10-12
L-22 | Learning & education | Foundations | html/foundations.html | Pending | P3 | M |  | learn/foundations |  | 2026-10-12
L-23 | Learning & education | Principles | html/principles.html | Pending | P3 | M |  | learn/principles |  | 2026-10-12
L-24 | Learning & education | Investor Mindset | html/investor-mindset.html | Pending | P3 | M |  | learn/investor-mindset |  | 2026-10-12
L-25 | Learning & education | Investor Profile | html/investor-profile.html | Pending | P3 | M |  | learn/investor-profile |  | 2026-10-12
L-26 | Learning & education | Financial DNA quiz | html/dna.html | Pending | P3 | M |  | learn/dna |  | 2026-10-12
L-27 | Learning & education | Mindset Simulator | html/mindset-sim.html | Pending | P3 | M |  | learn/mindset-sim |  | 2026-10-12
L-28 | Learning & education | Mindset Simulator hub | html/mindset-sim-hub.html | Pending | P3 | M |  | learn/mindset-sim-hub |  | 2026-10-12
L-29 | Learning & education | Train your mindset | html/train-mindset.html | Pending | P3 | M |  | learn/train-mindset |  | 2026-10-12
L-30 | Learning & education | Not money | html/not-money.html | Pending | P3 | M |  | learn/not-money |  | 2026-10-12
L-31 | Learning & education | Decision tools | html/decision.html | Pending | P3 | M |  | learn/decision |  | 2026-10-12
L-32 | Learning & education | Clarity | html/clarity.html | Pending | P3 | M |  | learn/clarity |  | 2026-10-12
L-33 | Learning & education | What-if scenarios | html/scenarios.html | Pending | P3 | M |  | learn/scenarios |  | 2026-10-12
L-34 | Learning & education | Life timeline | html/timeline.html | Pending | P3 | M |  | learn/timeline |  | 2026-10-12
L-35 | Learning & education | Fear roadmap | html/fear-roadmap.html | Pending | P3 | M |  | learn/fear-roadmap |  | 2026-10-12
L-36 | Learning & education | Roadmap | html/roadmap.html | Pending | P3 | M |  | learn/roadmap |  | 2026-10-12
L-37 | Learning & education | Roadmaps | html/roadmaps.html | Pending | P3 | M |  | learn/roadmaps |  | 2026-10-12
L-38 | Learning & education | Trader roadmap | html/trader-roadmap.html | Pending | P3 | M |  | learn/trader-roadmap |  | 2026-10-12
L-39 | Learning & education | Traditional roadmap | html/traditional-roadmap.html | Pending | P3 | M |  | learn/traditional-roadmap |  | 2026-10-12
L-40 | Learning & education | Simulator | html/simulator.html | Pending | P3 | M |  | learn/simulator |  | 2026-10-12
L-41 | Learning & education | Simulator guide | html/simulator-guide.html | Pending | P3 | M |  | learn/simulator-guide |  | 2026-10-12
L-42 | Learning & education | Simulator landing | html/simulator-landing.html | Pending | P3 | M |  | learn/simulator-landing |  | 2026-10-12
L-43 | Learning & education | Trading simulator | html/trading-simulator.html | Pending | P3 | M |  | learn/trading-simulator |  | 2026-10-12
L-44 | Learning & education | Trading coach | html/trading-coach.html | Pending | P3 | M |  | learn/trading-coach |  | 2026-10-12
L-45 | Learning & education | Trading brain | html/trading-brain.html | Pending | P3 | M |  | learn/trading-brain |  | 2026-10-12
L-46 | Learning & education | Know your finances | html/know-your-finances.html | Pending | P3 | M |  | learn/know-your-finances |  | 2026-10-12
L-47 | Learning & education | Financial being | html/financial-being.html | Pending | P3 | M |  | learn/financial-being |  | 2026-10-12
L-48 | Learning & education | Diagnostics | html/diagnostics.html | Pending | P3 | M |  | learn/diagnostics |  | 2026-10-12
L-49 | Learning & education | Life wealth | html/life-wealth.html | Pending | P3 | M |  | learn/life-wealth |  | 2026-10-12
L-50 | Learning & education | Impact | html/impact.html | Pending | P3 | M |  | learn/impact |  | 2026-10-12
L-51 | Learning & education | Impact detail | html/impact-detail.html | Pending | P3 | M |  | learn/impact-detail |  | 2026-10-12
M-01 | Markets & research | Markets: indices (NIFTY 50, SENSEX, IT, BANK) | html/markets.html | Done | P1 | S |  | (tabs)/markets | Live from the Arya backend; no invented prices offline | 2026-10-12
M-02 | Markets & research | Markets: sector indices (8 sectors) | html/markets.html | Done | P1 | S |  | (tabs)/markets | New /api/market/sectors route (needs a backend restart) | 2026-10-12
M-03 | Markets & research | Markets: FII / DII flows | html/markets.html | Blocked | P3 | S |  |  | No data source; the earlier hard-coded numbers were removed | 2026-10-12
M-04 | Markets & research | Equity detail | html/equitydetail.html | Pending | P3 | M |  | markets/equitydetail |  | 2026-10-12
M-05 | Markets & research | ETF detail | html/etfdetail.html | Pending | P3 | M |  | markets/etfdetail |  | 2026-10-12
M-06 | Markets & research | Mutual fund detail | html/mfdetail.html | Pending | P3 | M |  | markets/mfdetail |  | 2026-10-12
M-07 | Markets & research | Crypto detail | html/cryptodetail.html | Pending | P3 | M |  | markets/cryptodetail |  | 2026-10-12
M-08 | Markets & research | Commodity detail | html/commoditydetail.html | Pending | P3 | M |  | markets/commoditydetail |  | 2026-10-12
M-09 | Markets & research | Forex detail | html/forexdetail.html | Pending | P3 | M |  | markets/forexdetail |  | 2026-10-12
M-10 | Markets & research | F&O detail | html/fnodetail.html | Pending | P3 | M |  | markets/fnodetail |  | 2026-10-12
M-11 | Markets & research | Debt detail | html/debtdetail.html | Pending | P3 | M |  | markets/debtdetail |  | 2026-10-12
M-12 | Markets & research | Money market detail | html/moneydetail.html | Pending | P3 | M |  | markets/moneydetail |  | 2026-10-12
M-13 | Markets & research | Market intelligence | html/market-intel.html | Pending | P3 | M |  | markets/market-intel |  | 2026-10-12
M-14 | Markets & research | Market visualizer | html/market-visualizer.html | Pending | P3 | M |  | markets/market-visualizer |  | 2026-10-12
M-15 | Markets & research | Stock platform / screener | html/stock-platform.html | Pending | P2 | M |  | markets/stock-platform |  | 2026-10-12
M-16 | Markets & research | Options intelligence | html/options-intelligence.html | Pending | P3 | M |  | markets/options-intelligence |  | 2026-10-12
M-17 | Markets & research | QuantEdge | html/quantedge.html | Pending | P3 | M |  | markets/quantedge |  | 2026-10-12
M-18 | Markets & research | Hedge fund view | html/hedgefund.html | Pending | P3 | M |  | markets/hedgefund |  | 2026-10-12
M-19 | Markets & research | News feed + sentiment | html/news.html | Pending | P2 | M |  | markets/news |  | 2026-10-12
M-20 | Markets & research | CA advisor | html/ca-advisor.html | Pending | P3 | M |  | markets/ca-advisor |  | 2026-10-12
M-21 | Markets & research | Insurance directory | html/insurance-directory.html | Pending | P3 | M |  | markets/insurance-directory |  | 2026-10-12
S-01 | Portfolio & standalone apps | Portfolio: holdings list, live prices, SIP tab, insights | html/portfolio.html | Done | P1 | L |  | (tabs)/portfolio | On-device + Supabase holdings sync (untested against the live project) | 2026-10-12
S-02 | Portfolio & standalone apps | Portfolio: broker holdings CSV import (Zerodha / Groww) | js/finos-import.js | Done | P1 | M | 13 | tracker/holdings-import (Portfolio ⇪ Import) | Zerodha / Groww / generic CSV parsed identically to js/finos-import.js; rows become Portfolio holdings (replace units + avg cost, never add twice); holdings with no ticker/scheme code keep the broker price. CAS PDF import (S-03) still needs the document-ai backend. | 2026-10-12
S-03 | Portfolio & standalone apps | Portfolio: CAS statement import (PDF) | js/finos-import.js + document-ai/cas_import.py | Pending | P2 | L |  | portfolio/import | Needs the document-ai backend | 2026-10-12
S-04 | Portfolio & standalone apps | Portfolio Analyser: XIRR, sector heatmap, treemap | Porfolio Analyser/portfolio-analyser-v10.html | Pending | P2 | L |  | portfolio/analytics |  | 2026-10-12
S-05 | Portfolio & standalone apps | Portfolio Analyser: factor regression, Monte Carlo cones | Porfolio Analyser/portfolio-analyser-v10.html | Pending | P3 | L |  | portfolio/quant |  | 2026-10-12
S-06 | Portfolio & standalone apps | Portfolio Analyser: news sentiment, peers, promoter trend | Porfolio Analyser/portfolio-analyser-v10.html | Pending | P3 | L |  | portfolio/research |  | 2026-10-12
S-07 | Portfolio & standalone apps | Portfolio Analyser: watchlist & screener | Porfolio Analyser/portfolio-analyser-v10.html | Pending | P2 | M |  | portfolio/watchlist |  | 2026-10-12
S-08 | Portfolio & standalone apps | Portfolio Analyser: shareable link, themes, ⌘K palette | Porfolio Analyser/portfolio-analyser-v10.html | Not planned | P3 | M |  |  | Desktop-oriented | 2026-10-12
S-09 | Portfolio & standalone apps | TradeJournal (log, analytics, psychology, OCR scan) | TradeJournal/ | Pending | P3 | L |  | journal/ | Standalone app; own sync via a vault id | 2026-10-12
S-10 | Portfolio & standalone apps | News app (News1) | News1/ | Pending | P3 | M |  | markets/news | Separate Vite+Express service; npm advisories open | 2026-10-12
A-01 | Arya AI | Arya chat (streaming, profile context) | js/arya-ai.js | Done | P1 | M |  | (tabs)/arya | POST /api/chat SSE | 2026-10-12
A-02 | Arya AI | Arya: PULSE ranked insights (24 sections) | js/arya-sidebar-panel.js | Pending | P2 | L |  | arya/pulse | Ranking: js/arya-pulse-rank.js | 2026-10-12
A-03 | Arya AI | Arya: Plan / Map / Life tabs | js/arya-sidebar-panel.js + arya-roadmap.js | Pending | P3 | L |  | arya/plan |  | 2026-10-12
A-04 | Arya AI | Arya: Cal / India / Agent tabs | js/arya-sidebar-panel.js | Pending | P3 | L |  | arya/agent |  | 2026-10-12
A-05 | Arya AI | Arya: agent tools (33+, live quotes, analysis, scenarios) | js/arya-sidebar-panel.js | Pending | P2 | L |  | arya/tools | Backend tools exist; phone has no tool loop | 2026-10-12
A-06 | Arya AI | Arya: long-term memory & life events | js/arya-memory.js, arya-life-events.js | Pending | P3 | M |  | arya/memory |  | 2026-10-12
A-07 | Arya AI | Arya: safety guardrails on advice prompts | js/arya-guardrails.js | Done | P1 | S | 14 | (tabs)/arya | Same rules and wording as js/arya-guardrails.js (parity-tested on 420+ pairs); tax-evasion requests are refused on the phone before any network call; notes are appended to finished or stopped answers. | 2026-10-12
A-08 | Arya AI | Voice agent (speech in / out) | voiceagent/ | Pending | P3 | L |  | arya/voice | Mic permission is declared in app.json; no feature built | 2026-10-12
A-09 | Arya AI | Money AI page / chatbot brain / RAG filings | html/money-ai.html, chatbot/, rag-engine/ | Pending | P3 | L |  | arya/ |  | 2026-10-12
P-01 | Platform & account | Light / Bloomberg / Saffron themes | css/theme.css | Pending | P3 | M |  |  | Phone is dark-only | 2026-10-12
P-02 | Platform & account | Hindi UI (and lakh/crore units) | js/finos-i18n.js, js/i18n/hi.js | Pending | P2 | M |  |  |  | 2026-10-12
P-03 | Platform & account | Passcode lock + encrypted backups (vault) | js/finos-vault.js | Pending | P2 | L |  |  | Phone could use OS biometrics instead | 2026-10-12
P-04 | Platform & account | Global search (⌘K) | js/finos-search.js | Pending | P3 | S |  |  |  | 2026-10-12
P-05 | Platform & account | Alerts bell (alert engine, 14 rules) | js/finos-alerts.js, alerts/ | Pending | P2 | M |  |  | Backend runs on the user's machine | 2026-10-12
P-06 | Platform & account | Local notifications / background reminders | js/finos-reminders.js | Pending | P1 | L |  |  | Settings has a toggle with no effect | 2026-10-12
P-07 | Platform & account | Personalization: greetings, nudges, status strip | js/finos-personalization.js | Pending | P3 | M |  |  |  | 2026-10-12
P-08 | Platform & account | Onboarding + DNA quiz | html/onboarding.html, dna.html | Pending | P2 | L |  |  | Health score pillars for DNA/learning show neutral defaults | 2026-10-12
P-09 | Platform & account | Profile page | html/profile.html | Pending | P2 | S |  |  |  | 2026-10-12
P-10 | Platform & account | Google sign-in | js/auth.js | Pending | P3 | S |  |  | Enabled on the Supabase project | 2026-10-12
P-11 | Platform & account | Feedback loop + usage opt-in | js/finos-feedback.js | Pending | P3 | M |  |  |  | 2026-10-12
P-12 | Platform & account | Settings parity (every preference takes effect) | html/settings.html | Done | P2 | M |  |  | The no-effect 'Price Alerts' switch was removed; Settings now says reminders are not available and points to the Financial calendar. Name, income and backend host all take effect. | 2026-10-12
P-13 | Platform & account | Export / backup my data | html/settings.html | Done | P1 | S |  |  | Privacy & your data → Export my data (JSON; sign-in tokens never included). | 2026-10-12
P-14 | Platform & account | Login, sign-up, sign-out (email + password) | js/auth.js | Done | P1 | M |  |  | Built; real sign-in untested against the live project | 2026-10-12
P-15 | Platform & account | Tracker sync with the website (three-way merge) | js/finos-tracker-sync.js | Done | P1 | L |  |  | Built and tested against mocks; needs the live table | 2026-10-12
P-16 | Platform & account | Holdings cloud sync | supabase/holdings.sql | Done | P1 | M |  |  | Built and tested against mocks; needs the live table | 2026-10-12
R-01 | Release readiness | Run supabase/profiles_rls.sql (closes the open profiles table) | supabase/profiles_rls.sql | Blocked | P0 | S | 1 |  | Needs the user's Supabase dashboard login — 13 profile rows were readable with the public key | 2026-10-12
R-02 | Release readiness | Run core_tables.sql, holdings.sql, tracker_snapshot.sql | supabase/ | Blocked | P0 | S | 1 |  | Needs the user's Supabase dashboard login | 2026-10-12
R-03 | Release readiness | Real sign-in + sync test on the live project | mobile/ | Blocked | P0 | S | 1 |  | Needs the SQL above and the user's credentials | 2026-10-12
R-04 | Release readiness | Privacy & consent screen (what is stored, what is shared, switches) | html/privacy.html, js/finos-privacy.js | Done | P0 | M | 2 |  | Built: what is on the phone (live counts), every data flow, never-do list, permissions, export / erase. Guard tests fail if a new host or permission appears. Operator details left blank on purpose. | 2026-10-12
R-05 | Release readiness | Terms of use screen | html/terms.html | Done | P0 | S | 2 |  | Port of html/terms.html, kept as a draft for legal review; operator/liability/law not invented. | 2026-10-12
R-06 | Release readiness | Account deletion + data erase | — | Partial | P0 | M | 2 |  | App side built and tested (erase phone, delete cloud copy, delete account via RPC). Needs supabase/delete_account.sql run on the live project before 'Delete my account' works. | 2026-10-12
R-07 | Release readiness | Restart Arya backend (new key + sector route) | arya-ai/ | Blocked | P0 | S | 1 |  | Old process is still running without the new code | 2026-10-12
R-08 | Release readiness | EAS device build (iOS + Android) | mobile/eas.json | Blocked | P0 | M |  |  | Needs Apple/Google credentials | 2026-10-12
R-09 | Release readiness | Real-device test of file picker, share, keyboard, safe areas | mobile/ | Pending | P0 | M |  |  | Everything so far ran in the web preview | 2026-10-12
R-10 | Release readiness | Push / local notification permission flow | — | Pending | P1 | M |  |  |  | 2026-10-12
R-11 | Release readiness | App icon, splash, screenshots, store listing | mobile/assets | Pending | P1 | M |  |  | Placeholders only | 2026-10-12
R-12 | Release readiness | Accessibility pass (labels, contrast, large text) | — | Partial | P1 | M |  |  | Static pass done and guarded by __tests__/a11y.test.mts: every touchable/input has a role or label, icon-only buttons are labelled, text colours reach 4.5:1 (textDim raised from 2.6:1, purple text uses purpleInk), system font scaling is left on. Not yet tried with VoiceOver / TalkBack on a device. | 2026-10-12
R-13 | Release readiness | Crash reporting + opt-in analytics | — | Pending | P2 | M |  |  |  | 2026-10-12
R-14 | Release readiness | Offline behaviour for markets and chat | — | Pending | P2 | M |  |  |  | 2026-10-12
R-15 | Release readiness | Test coverage for React screens | mobile/__tests__/ | Pending | P2 | L |  |  | Pure logic is covered (51 tests); screens are verified by hand in the preview | 2026-10-12
R-16 | Release readiness | Run supabase/delete_account.sql (enables 'Delete my account') | supabase/delete_account.sql | Blocked | P0 | S | 1 |  | Needs the user's Supabase dashboard login | 2026-10-12
R-17 | Release readiness | Declare only the permissions the app uses (no mic / camera / speech) | mobile/app.json | Done | P0 | S |  |  | Removed unused microphone, camera and speech permissions and the expo-av plugin; a test now fails if they return | 2026-10-12

## Build order
Order | ID | Feature | Area | Priority | Effort | Phone status | Notes
1 | R-01 | Run supabase/profiles_rls.sql (closes the open profiles table) | Release readiness | P0 | S | Blocked | Needs the user's Supabase dashboard login — 13 profile rows were readable with the public key
1 | R-02 | Run core_tables.sql, holdings.sql, tracker_snapshot.sql | Release readiness | P0 | S | Blocked | Needs the user's Supabase dashboard login
1 | R-03 | Real sign-in + sync test on the live project | Release readiness | P0 | S | Blocked | Needs the SQL above and the user's credentials
1 | R-07 | Restart Arya backend (new key + sector route) | Release readiness | P0 | S | Blocked | Old process is still running without the new code
2 | R-04 | Privacy & consent screen (what is stored, what is shared, switches) | Release readiness | P0 | M | Done | Built: what is on the phone (live counts), every data flow, never-do list, permissions, export / erase. Guard tests fail if a new host or permission appears. Operator details left blank on purpose.
2 | R-05 | Terms of use screen | Release readiness | P0 | S | Done | Port of html/terms.html, kept as a draft for legal review; operator/liability/law not invented.
2 | R-06 | Account deletion + data erase | Release readiness | P0 | M | Partial | App side built and tested (erase phone, delete cloud copy, delete account via RPC). Needs supabase/delete_account.sql run on the live project before 'Delete my account' works.
3 | T-26 | Retirement Planner (Monte Carlo success odds) | Trackers & planners | P1 | L | Done | Built: corpus by source, 25× need, gap, income, Monte Carlo odds, fan chart, SIP solver. Engine identical to js/finos-montecarlo.js (40 random configs) and plan arithmetic identical on 400 random profiles.
4 | T-31 | Tax (regime compare, Tax Savings Tracker, Tax Planner) | Trackers & planners | P1 | L | Done | Savings tracker (headroom per section) and the full Tax Planner (both regimes with surcharge, HRA, 80C/80D/NPS/24(b), LTCG/STCG, action list); parity-tested vs js/finos-tax-calc.js. Web surcharge fixed in the same pass (taxable income, new-regime top rate 25%).
5 | T-27 | Salary Optimizer (CTC restructure) | Trackers & planners | P1 | M | Done | CTC breakup → gross, HRA three-way minimum, tax in both regimes, take-home, restructuring tips; parity-tested. Take-home becomes income only on tap (the website overwrites finos_monthly_income on every render).
6 | T-28 | SIP Step-Up Planner | Trackers & planners | P1 | S | Done | Flat vs stepped-up SIP, scenario cards (5/10/15/20%), corpus chart, year table, milestones; parity-tested vs js/finos-sip-stepup.js incl. out-of-range inputs
7 | T-06 | Debt Optimizer (avalanche / snowball) | Trackers & planners | P1 | M | Done | Avalanche vs snowball + home-loan prepayment impact; shares balances with Net Worth; parity-tested vs js/finos-debt-optimizer.js
8 | T-14 | Home Loan EMI Planner | Trackers & planners | P1 | M | Done | EMI, amortisation, affordability, 24(b)/80C deductions, prepayment impact; parity-tested. Website's PMAY-CLSS 'eligible' banner deliberately not ported (scheme bands ended); writes loan keys only on 'Save as my home loan'.
9 | T-09 | Fixed Income (FD) Tracker | Trackers & planners | P1 | M | Done | FD, RD, PPF, NSC, SCSS, Sukanya, bonds, post office; same finos_fd_portfolio key as the web; parity-tested; RD 0% division guarded
10 | T-13 | Gold Tracker | Trackers & planners | P1 | M | Done | Physical, SGB, gold ETF, gold MF; user-typed price only (no invented rate); coupon; parity-tested vs js/finos-gold-tracker.js
11 | T-10 | Financial Calendar (+ reminders) | Trackers & planners | P1 | L | Partial | Month grid, day detail, coming-up list, summary cards: SIP, deposit maturities (real terms), insurance, goals, subscriptions, tax dates; parity-tested. Phone notifications NOT built: need an OS notification permission, which the privacy guard test currently forbids (owner decision).
12 | T-33 | Future Loss / System Leak | Trackers & planners | P1 | M | Done | Monthly leak from the ledger + subscriptions, 10/20/30-year future value, redirect share; parity-tested vs js/finos-leak.js
13 | S-02 | Portfolio: broker holdings CSV import (Zerodha / Groww) | Portfolio & standalone apps | P1 | M | Done | Zerodha / Groww / generic CSV parsed identically to js/finos-import.js; rows become Portfolio holdings (replace units + avg cost, never add twice); holdings with no ticker/scheme code keep the broker price. CAS PDF import (S-03) still needs the document-ai backend.
14 | A-07 | Arya: safety guardrails on advice prompts | Arya AI | P1 | S | Done | Same rules and wording as js/arya-guardrails.js (parity-tested on 420+ pairs); tax-evasion requests are refused on the phone before any network call; notes are appended to finished or stopped answers.
Order 1 items need the owner (Supabase dashboard / device credentials). The rest are built in sequence, top to bottom.

## Build log
Date | ID(s) | What was built | Verification | Tests after
2026-10-04 | T-03, C-64, C-79 | Subscription Tracker; Prepay-or-Invest; Job Offer Comparer | Parity tests vs the website; preview run | 22
2026-10-11 | P-15, P-16 | Tracker sync (three-way merge) + holdings sync; website sync upgraded to v2 | Phone engine vs website module; PostgREST-rules server; mock-Supabase UI run | 33
2026-10-11 | M-01, M-02 | Live sector indices; removed invented index prices, FII/DII and Account Aggregator demos | Route verified in-process (8 sectors from NSE) | 33
2026-10-12 | T-34 | Bank statement import (CSV / AA JSON): preview, dedupe, undo | 700 random statements identical to the website; preview run | 43
2026-10-12 | T-32 | Money Score: six pillars, ranked next moves, what-if, history | 1,500 random inputs identical to the website; preview run | 51
2026-10-12 | R-04, R-05, R-06, R-17 | Privacy & your data screen, Terms of use, export / erase / delete cloud copy / delete account (RPC); removed unused phone permissions | 63 tests incl. guards (no new host, no new permission, no analytics SDK); preview run: counts, export without token, erase | 63
2026-10-12 | T-26 | Retirement planner: projected corpus vs 25× need, Monte Carlo success odds (4,000 futures), fan chart, monthly-SIP solver | Engine seeded-identical to the website on 40 configs; solveContribution identical (24,500 on the preview profile); plan identical on 400 random stored profiles | 68
2026-10-12 | T-31 (savings tracker), T-33, T-09, T-06 | Tax Savings (deduction headroom vs regime), Future Loss, Deposits & fixed income, Debt payoff (avalanche / snowball) | savingsPlan identical to the website on 2,000 random cases; leak on 800 ledgers; FD on 1,500 entries; debt on 600 loan sets; preview run of all four screens | 94
2026-10-12 | T-27, T-28, T-14 | Salary structure (CTC → take-home, HRA, tips), SIP step-up planner, Home loan EMI & prepayment planner | Salary 1,500 random salaries + tips identical to the website; step-up 1,500 inputs incl. junk; home loan 1,200 loans + prepayment; preview run of all three screens | 127
2026-10-12 | T-13, T-10 (calendar view) | Gold tracker; Financial calendar (month grid, upcoming, summary) | Gold total/coupon identical to the website on 400 portfolios; calendar events identical on 150 random households with a frozen clock; tax dates identical over 4 ranges; preview run | 134
2026-10-12 | S-02, A-07 | Broker holdings CSV import (preview, replace-not-add, undo-safe); Arya safety guardrails | Holdings parser identical to the website on 700 random files; guardrails identical on 405 user×reply pairs; preview run: import into Portfolio, evasion refused with no /api/chat request, normal answer streams | 146
2026-10-12 | T-04, T-05 | Credit score tracker; Crypto tracker (found in the tree from a parallel session, verified and logged here) | Both screens rendered in the preview without console errors; their parity tests are part of the 146 | 146
2026-10-12 | T-31 (Tax Planner) | Tax Planner: both regimes side by side with surcharge, HRA, deductions, capital gains and actions; website surcharge corrected | Identical to the website on 1,500 random taxpayers (incl. 100+ above ₹50L); agrees with the shared tax core up to ₹50L; website tax-consistency tests pass; preview run | 152
2026-10-12 | R-12, P-12 | Accessibility pass (labels, roles, contrast, guard test); Settings no longer shows a toggle that does nothing | a11y guard test (4 checks); contrast computed against the theme; preview run of Settings | 156
2026-10-12 | T-30 | Bonus & windfall allocator | Waterfall identical to the website on 1,000 random households; bonus tax figures equal what the website prints; preview run | 161
2026-10-12 | T-22 | Passive income tracker | Total and coverage identical to the website's _recompute on 800 random stream lists; preview run | 167
2026-10-12 | T-17 | Life cover needed calculator (linked from Insurance) | Identical to the website on 1,500 random profiles incl. equal discount/inflation; preview run | 170
2026-10-12 | T-23 | Portfolio rebalancer | Class rows, normalised target and drift flag identical to the website on 1,000 portfolios; preview run | 175
2026-10-12 | T-16 | ITR prep kit (linked from the Tax planner) | Every figure identical to the website's _compute on 800 random sets of stored values with a frozen clock; preview run | 179
2026-10-12 | T-12 | Goal optimizer (linked from Goals); website double-counted inflation on saved money and was fixed | Identical to the corrected website on 800 random goal sets with a frozen clock; website suite 327/327; preview run | 183

## Legend
Term | Meaning
Phone status | Done = built, tested, verified in the preview. Partial = part of the website feature exists. Pending = not started. Blocked = needs something only the owner can provide. Not planned = deliberately left out.
Priority | P0 release blocker · P1 high value for daily use · P2 useful · P3 long tail
Effort | S = under a day · M = one to three days · L = more than three days (rough, for ordering only)
Build order | 1 = owner actions that unblock everything · 2 = store-required screens · 3 onward = the next ports, top to bottom
Done means | Pure logic ported with a parity test against the website's own module, storage covered by tests, and the screen exercised in the browser preview. Not yet run on a physical device.
Editing | Change 'Phone status' with the dropdown; the Summary and Build order sheets recalculate.
Source | Counts come from files on disk on 2026-10-12: 123 pages in html/, 90 calculators, 30 Command Hub entries in js/finos-search.js.